## April 28, 2020 Status Log
4% (Non-Competitive) Housing Tax Credit Program 2020 Application Status Log
Updated as of: |  |  | 2020-04-28
1Based on applicant selection in the application. Subject to change. If Application Status column reflects "Pre-application" then Board Meeting Date is the meeting at which the Inducement Resolution will be considered which applies to TDHCA as bond issuer transactions only.
2"Approved" means approved by the TDHCA Board. "Active" means the application is under review. "Closed" means the transaction has closed on the bond financing. "Withdrawn" means the application has been withdrawn and is not under review. "Pre-application" means TDHCA is the bond issuer and a pre-application was submitted for consideration of an Inducement Resolution.
3An amount will only be reflected here if TDHCA is the bond issuer. For all local issuer transactions the cell will reflect "N/A". The bond issuer is the entity recommending the amount of bonds to be issued.
TDHCA # | Previous TDHCA # | Development Name | Development City | Development County | Development Region | Full Application Submission Date (MM/DD/YYYY) | Board Meeting Date (MM/DD/YYYY) | Application Status | Construction Type | Target Population | Total Units | Total Low-Income Units | Bond Reservation Date (MM/DD/YYYY) | Bond Expiration Date (MM/DD/YYYY) | Bond Reservation Amount | Bond Issuer | Requested HTC Amount | Recommend HTC Amount | Recommend Bond Amount | Direct Loan Request (Y/N) | Development Address | Development ZIP Code | Applicant Contact | Applicant Phone | Applicant Email | Bond Issuer Contact | Bond Issuer Phone
20400 |  | Palladium at West Francis | Midland | Midland | 12 | 2020-12-03 | 2020-05-21 | Active | NC | General | 240 | 188 | 2020-01-06 | 2020-07-04 | 25000000 | Midland County PFC | 1499588 |  |  | Y | 1707 W Francis | 79701 | Tom Huth | (972) 774-4400 | tom@palladiumusa.com | Jeanette Castaneda | (432) 570-4155
comment | 2020-01-07 | Not competitive for DL. Once log is finalized Andrew will send an email letting them know we have no more money and they'll need to withdraw the request and revise the 4% app to include an alternative funding source. Will do that this week or next week. Once the app is revised we'll do a program review.
20401 |  | Palladium Port Aransas | Port Aransas | Aransas | 10 | 2019-12-13 | 2020-04-23 | Approved | NC | General | 183 | 165 | 2020-01-02 | 2020-06-30 | 19000000 | Port Aransas PFC | 1155074 | 1155074 | 0 | Y | Highway 361 and Charlie's Pasture South Trail | 78373 | Tom Huth | (972) 774-4400 | tom@palladiumusa.com | David Parsons | (361) 749-4111
comment
20417 |  | St. Joe Apartments | Houston | Harris | 6 | 2019-12-13 | 2020-04-23 | Withdrawn | NC | General | 307 | 307 | 2020-01-02 | 2020-06-30 | 51757648 | Houston HFC | 4596000 |  |  | N | 801 St. Joseph Parkway | 77022 | Kip Platt | (972) 385-4101 | kplatt@providentrealty.net | Jeff Smith | (713) 461-2749
comment | 2019-12-18 | Notified applicant that application could be terminated based on how incomplete it was. They plan on re-submitting.
| 2020-01-31 | Sent email to applicant following up on when they plan on re-submitting.
| 2020-02-07 | Noticed on the BRB website that the bond reservation has been withdrawn. Will consider the HTC application withdrawn.
20412 |  | 1604 Lofts Apartments | San Antonio | Bexar | 9 | 2019-12-13 | 2020-05-21 | Active | NC | General | 324 | 324 | 2020-01-02 | 2020-06-30 | 38000000 | Las Varas PFC | 1899524 |  |  | N | NWC 1604 Loop E and Weichold Road | 78109 | David Nisivoccia | (210) 477-6262 | executiveoffice@saha.org | David Nisivoccia | (210) 477-7802
comment | 2020-03-18 | Phone call with Debra and Jason. They plan on withdrawing the request for Direct Loan. Will submit revised application exhibits. Let REA know that they'll be "officially" transferred when those exhibits are received and inserted into the application.
20414 |  | The Arbor at Wayforest | Houston | Harris | 6 | 2019-12-13 | 2020-03-26 | Closed | NC | General | 192 | 192 | 2020-01-02 | 2020-06-30 | 20000000 | Harris County Housing Authority PFC | 1262807 | 1262807 |  | N | SEQ of Wayforest Dr. and Richcrest Dr. | 77060 | Dan Wilson | (305) 357-4733 | dwilson@apcompanies.com | Horace Allison | (713) 669-4512
comment | 11 22 2019 | Has an undesirable and neighborhood risk factors
20407 |  | New Hope Housing Avenue J Apartments | Houston | Harris | 6 | 2019-11-21 | 2020-02-20 | Approved | NC | Supportive Housing | 100 | 100 | 2020-01-02 | 2020-06-30 | 23000000 | Houston HFC | 1290647 | 1290467 |  | N | SWC Avenue J and Engel Street (5220 Avenue J) | 77011 | Joy Horak-Brown | (713) 222-0290 | joy@newhopehousing.com | Jeff Smith | (713) 461-2749
comment | 2020-01-24 | Need no objection resolution, 2020 certifications, confirmation on parking variance granted, purchase contract extension and confirmation of CDBG or HOME allocation to this deal. Term sheet indicated closing had to take place by date certain or funds could be allocated to another deal.
20405 |  | Gala at Fate | Fate | Rockwall | 3 | 2019-12-13 | 2020-05-21 | Active | NC | Elderly | 185 | 185 | 2020-03-03 | 2020-08-30 | 25000000 | North Central Texas HFC | 1173150 |  |  | N | East end of Black Oak Lane | 75189 | Ryan Combs | (512) 983-0422 | rcombs@gardenercapital.com | Tim Nelson | (512) 481-2022
comment | 2020-02-12 | Ryan indicated he'll be withdrawing the Direct Loan request. I suggested he revise all affected exhibits in the application and completely re-submit a new PDF and Excel version. Once he uploads he should notify staff and we'll start the review. Because his reservation expires at the end of June I suggested it's possible we can prioritize for the May meeting.
| 2020-02-27 | Ryan indicated he'll be withdrawing the current bond reservation and having a new one issued. It shouldn't affect anything on our end. Asked for an update on timing and whether the Board date should be pushed out if closing has been delayed.
| 2020-04-24 | Call from Coats Rose (Paige?) indicated there was a new entity in the org chart (but not likely to be new principals) and a change to the unit mix. Someone (don't remember who) was going to require more 2BR/2BA so some of the 1BR/1BA units were going to be converted. I suggested the applicant provide us with a summary of the changes and revised exhibits so we can evaluate.
20408 |  | Vi Collina | Austin | Travis | 7 | 2019-12-13 | 2020-04-23 | Approved | NC | General | 170 | 170 | 2020-01-02 | 2020-06-30 | 24000000 | Austin HFC | 1340220 | 1340220 | 0 | N | 2401 E. Oltorf St. (aka 2431 e. Oltorf St.) | 78741 | Lisa Stephens | (352) 213-8700 | lisa@saigebrook.com | Mark Malveaux | (214) 754-9221
comment | 2020-01-24 | Per Gregg - they plan on submitting revised org docs to add an entity for a property tax exemption. Will need to send PPR by 2/28/2020. Might prompt other changes to financing exhibits.
| 2020-02-03 | Applicant sent email stating they plan on making changes to the application - property tax exemption, adding 30% units and city of Austin as a partner.
| 2020-04-02 | Received all changes to application. Also received signed copy of resolution.
20406 |  | Gala at Central Park Apartments | Hurst | Tarrant | 3 | 2019-12-13 | 2020-05-21 | Active | NC | Elderly | 94 | 94 | 2020-01-03 | 2020-07-01 | 15000000 | Hurst PFC | 486783 |  |  | Y | S side of W. Pipeline Rd., W of Buena Vista Dr. | 76053 | Ryan Combs | (512) 983-0422 | rcombs@gardnercapital.com | Clay Caruthers | (817) 788-7026
comment | 2020-04-24 | Bond reservation was withdrawn. Sent email to applicant who indicated they needed more time to close. Reached out to REA to determine if May was possible from an underwriting perspective or if we should hold off until June.
comment | 2020-02-07 | Noticed on the BRB website that the bond reservation has been withdrawn. Sent email to applicant confirming that the HTC application should be withdrawn.
| 2020-02-10 | Applicant indicated they are not withdrawing the HTC application. They are increasing the bond amount as a result of higher construction costs. They hope to get a reservation out of the collapse. Will now target an April meeting; let REA know.
| 2020-04-20 | Applicant withdrew bond pre-app with TDHCA. Called to state the bond reservation would be issued this week. Has updates to the application that they'll try and submit by Thursday/Friday this week. Diamond will review to see if she can still get the report ready by REA review deadline to make the May meeting. We'll circle back with the applicant and let him know.
20404 |  | Tampico Apartments | San Antonio | Bexar | 9 | 2019-12-13 | 2020-03-26 | Approved | NC | General | 200 | 136 | 2020-01-03 | 2020-07-01 | 23000000 | Las Varas PFC | 739670 | 739670 |  | N | 200 Tampico St. | 78207 | Holly Thoman | (210) 354-3705 | Holly@missiondg.com | Timothy Alcott | (210) 477-6633
comment
20611 | 20402 | 333 Holly | The Woodlands | Montgomery | 6 | 2019-12-27 | 2020-05-21 | Active | Acq/Rehab | General | 332 | 332 | TBD | TBD | 36800000 | TDHCA | 2513320 |  |  | N | 333 Holly Creek Court | 77381 | Wes Larmore | (213) 634-1566 | wlarmore@related.com | Teresa Morales | (512) 475-3344
comment | 2020-03-06 | Based on timing of receipt of No Objection Resolution this deal will likely need a waiver of the 14-day deadline.
| 2020-04-02 | Deal will be re-routed through TDHCA as issuer. Will need changes to organizational structure (Rainbow Housing) and changes to other financing exhibits as a result. Need to assign new app ID number, too.
20410 |  | Traders Flats | San Antonio | Bexar | 9 | 2019-12-13 | 2020-05-21 | Active | NC | General | 324 | 324 | 2020-01-03 | 2020-07-01 | 38000000 | Las Varas PFC | 1846377 |  |  | N | 8671 SW Loop 410 | 78252 | David Nisivoccia | (210) 477-6262 | executiveoffice@saha.org | David Nisivoccia | (210) 477-6262
comment | 2020-03-18 | Phone call with Debra and Jason. They plan on withdrawing the request for Direct Loan. Will submit revised application exhibits. Let REA know that they'll be "officially" transferred when those exhibits are received and inserted into the application.
20416 |  | The Estates at Owen Tech | Austin | Travis | 7 | 2019-12-13 | 2020-05-21 | Active | NC | Elderly | 174 | 174 | 2020-01-03 | 2020-07-01 | 20000000 | Austin Affordable PFC, Inc. | 1239589 |  |  | Y | 14101, 14011 and 14008 Owen-Tech Blvd. | 78728 | Adrian Iglesias | (512) 971-9127 | aiglesias@GHDevelopment.com | Ron Kowal | (512) 767-7792
comment | 2020-01-07 | Not competitive for DL. Once log is finalized Andrew will send an email letting them know we have no more money and they'll need to withdraw the request and revise the 4% app to include an alternative funding source. Will do that this week or next week. Once the app is revised we'll do a program review.
| 2020-02-14 | Call with Audrey and she indicated they are moving forward without the Direct Loan request. She'll revise all the exhibits in the application and submit a whole new app for us to start reviewing. Suggested she send Andrew an email withdrawing the DL request. I let Andrew know all of this.
| 2020-03-07 | Emailed Audrey asking what her intentions are with the application since it isn't competitive for Direct Loan.
20409 |  | McKinney Flats | McKinney | Collin | 3 | 2019-12-13 | 2020-03-26 | Approved | NC | General | 205 | 205 | 2020-01-03 | 2020-07-01 | 32000000 | McKinney HFC | 1393849 | 1393849 |  | N | Collin McKinney Parkway at Test Drive | 75070 | Cristel Todd | (972) 547-7519 | ctodd@mckinneytexas.org | Cristel Todd | (972) 547-7519
comment
20612 | 20403 | The Pines | The Woodlands | Montgomery | 6 | 2019-12-27 | 2020-05-21 | Active | Acq/Rehab | General | 152 | 152 | TBD | TBD | 22000000 | TDHCA | 1465042 |  |  | N | 3451 Tangle Bush Drive | 77381 | Wes Larmore | (213) 634-1566 | wlarmore@related.com | Teresa Morales | (512) 475-3344
comment | 2020-03-06 | Based on timing of receipt of No Objection Resolution this deal will likely need a waiver of the 14-day deadline.
| 2020-04-02 | Deal will be re-routed through TDHCA as issuer. Will need changes to organizational structure (Rainbow Housing) and changes to other financing exhibits as a result. Need to assign new app ID number, too.
20411 |  | Kitty Hawk Flats Apartments | San Antonio | Bexar | 9 | 2019-12-13 | TBD | Active | NC | General | 239 | 239 | 2020-04-21 | 2020-10-18 | 28000000 | Las Varas PFC | 1482838 |  |  | Y | NWC of O'Connor Rd. and Kitty Hawk Rd. | 78109 | David Nisivoccia | (210) 477-6262 | executiveoffice@saha.org | David Nisivoccia | (210) 477-6262
comment | 2020-03-04 | Noticed on BRB website the reservation was withdrawn on 2/19/2020. Discussed next steps with Andrew and Marni. Issue not resolved.
| 2020-03-05 | Emailed Sarah and Jason asking what theire intentions are with the HTC application since there is no reservation. Waiting on response.
| 2020-03-18 | Phone call with Debra and Jason. They will likely be withdrawing the HTC and Direct Loan application. Will confirm with the applicant and let us know early next week. Plan to pursue the development later in the summer/fall.
| 2020-04-21 | Application received a new reservation. Will follow-up with Andrew on what it means for Direct Loan.
20418 |  | Park at 38 Thirty (fka Artisan at Parkdale) | San Antonio | Bexar | 9 | 2019-12-13 | 2020-03-26 | Approved | NC | General | 196 | 196 | 2020-01-06 | 2020-07-04 | 25000000 | San Antonio Housing Trust Finance Corporation | 1027837 | 1027837 |  | N | 3830 Parkdale St. | 78229 | Lucila Diaz | (210) 408-3152 | lucila@franklindev.net | Pedro Alanis | (210) 735-2772
comment
20413 |  | Residences at Merritt Hill | Rowlett | Dallas | 3 | 2019-12-13 | 2020-05-21 | Active | NC | General | 260 | 260 | 2020-01-06 | 2020-07-04 | 33000000 | Rowlett HFC | 1888671 |  |  | N | SE of intersection of Merritt Rd. & Pres George Bush Turnpike | 75089 | Gary Lacey | (972) 815-5500 | glacey@nurock.com | Rick Sheffield | (469) 431-0108
comment | 2020-01-24 | Has a market study that doesn't comply with the rules. REA sent an email on 1/24/20 explaining that the deadline to resolve is 2/14/20 and after this date the application would be terminated.
| 2020-02-12 | Market study issue resolved. Applicant needs more time in obtaining the no objection resolution. Will be moved to the April meeting.
| 2020-03-25 | Email from applicant requesting to be moved to May meeting. Notified REA.
20600 |  | Oaks on Clark | San Antonio | Bexar | 9 | 2020-01-02 | 2020-04-23 | Approved | Acq/Rehab | General | 80 | 80 | 2020-04-08 | 2020-10-05 | 10000000 | TDHCA | 607290 | 597284 | 10000000 | N | 4622 Clark Avenue | 78223 | Wes Larmore | (213) 634-1566 | wlarmore@related.com | Teresa Morales | (512) 475-3344
comment
20601 | 19611 | Granada Terrace Apartments | Houston | Harris | 6 | 2019-12-13 | 2020-04-23 | Approved | Acq/Rehab | General | 156 | 156 | 2020-04-15 | 2020-10-12 | 16000000 | TDHCA | 882061 | 882061 | 16000000 | N | 1301 Avenue A | 77587 | Robert Budman | (323) 302-9610 | rob@blvdcapitalinvestment.com | Teresa Morales | (512) 475-3344
comment | 2020-01-28 | Requested clarification from applicant on accessible route connecting all accessible units to all amenities.
| 2020-04-02 | Issue with accessible route resolved.
20603 | 19612 | Scott Street Lofts | Houston | Harris | 6 | 2019-12-13 | 2020-05-21 | Active | NC | Elderly | 123 | 98 | TBD | TBD | TBD | TDHCA | 678924 | 0 | 0 | N | 1320 Scott Street | 77003 | David Mark Koogler | (281) 292-1958 | dkoogler@mark-dana.com | Teresa Morales | (512) 475-3344
comment | 2020-01-21 | Timing issues with city of Houston for permits. Applicant doesn't think permits will happen until May. Moving to April Board meeting. Will seek bond reservation in February. Applicant believes he has team lined up to start conference calls.
| 2020-04-02 | Applicant still working through timing with city and CDBG docs. Made decision to move to May meeting. Notified REA. Need to have follow-up conversation with Elizabeth and borrower regarding concerns with the structure.
20420 |  | Pan American Apartments | San Antonio | Bexar | 9 | 2020-01-14 | 2020-04-23 | Approved | Acq/Rehab | General | 100 | 100 | 2020-01-13 | 2020-07-11 | 15000000 | San Antonio Housing Trust Finance Corporation | 674355 | 674355 | 0 | N | 143 NW 36th Street | 78237 | Paul Moore | (303) 226-9111 | pmoore@monroegroup.com | Pedro Alanix | (210) 299-3530
comment | 2020-01-06 | Fee only submitted, BRB reservation hasn’t been issued yet, therefore they cannot submit the application.
20421 | 19442 | Richcrest Apartments | Houston | Harris | 6 | 2019-10-16 | 2020-03-26 | Approved | NC | General | 288 | 286 | 2020-01-13 | 2020-07-11 | 30000000 | Victory Street PFC | 1974441 | 1974441 |  | N | SEC Imperial Valley Dr & Richcrest Dr | 77060 | David Yarden | (818) 706-0694 | dyarden@amcalhousing.com | Tory Gunsolley | (713) 260-0800
comment | 2019-12-18 | Needs a reservation. Not sure if that will happen in January or March. Likely to just supplement 2019 application with 2020 certifications.
| 2019-12-20 | Need to look at crime issue.
| 2020-01-07 | Re-ran the Neighborhood Scout report and crime is at 14.03 so it's not an issue.
| 2020-01-24 | Need site control extension; no objection resolution from county and 2020 certifications. Sent email to applicant.
| 2020-02-07 | Everything was received and inserted into the application.
20605 | 19608 | Reserve at San Marcos | San Marcos | Hays | 7 | 2019-09-20 | 2020-03-26 | Approved | NC | General | 376 | 320 | 2020-02-25 | 2020-08-23 | 41000000 | TDHCA | 1857733 | 1857733 | 41000000 | N | SWC of Hwy 123 & Monterry Oak | 78666 | Noor Jooma | (469) 855-6662 | noorjooma@gmail.com | Teresa Morales | (512) 475-3344
comment | 2019-09-17 | Talked with Julie and Noor. They're working on submitting the HTC application on 9/20/19 to make the December Board meeting. Will evaluate the financial impact of the additional costs associated with a new reservation. Trying to make the January closing - thinks city can deliver permits in December. Explained the benefit of withdrawing AFTER carryforward has been filed (forfeit last of BRB filing fees) given number of applications planned for January reservations.
| 2019-09-17 | In conversations with Julie, the city approved the No Objection Resolution conditioned upon the development providing shuttle service 3x per week to area amenities (retail, grocery, etc.) because they believe the property is too far from such amenities and there is no public transportation.
| 2019-10-14 | Applicant indicated they are considering options from equity providers. May not go with PNC as represented in the application.
| 2019-11-04 | Applicant indicated they will likely go with CREA as equity investor. We'll target the January meeting and will issue a 2020 reservation but file carryforward on the 2019 reservation. Indicated I would reduce the closing fee as a result of the carryforward in order to preserve the volume cap. Need to discuss the bond underwriter planned for the deal (Sturgis) with Monica and Barton.
| 2019-12-11 | Sent email to Juli asking for an update on whether they're still looking for the January meeting and if they've selected an equity investor.
| 2020-01-07 | Email from Juli indicated they'll be looking at the April Board meeting based on status of KeyBank and CREA. Let REA know.
| 2020-01-09 | Applicant changed their mind. Now looking to target the March meeting. Let REA know.
| 2020-01-28 | Received new term sheets. Still need updates to financing exhibits as a result. Also requested the 2020 certifications.
20606 | 19610 | Fish Pond at Corpus Christi | Corpus Christi | Nueces | 10 | 2019-09-06 | 2020-06-25 | Active | NC | Elderly | 112 | 111 | 2020-01-22 | 2020-07-20 | 10000000 | TDHCA | 675744 | 0 | 0 | Y | 1006 Sixth Street | 78404 | David Fournier | (512) 970-3889 | dfournier@fishpondliving.com | Teresa Morales | (512) 475-3344
comment | 2019-08-07 | Applicant intends to purchase the land prior to 8/31/19 when the current contract expires.
| 2019-10-09 | Did they purchase the land? What is timeline now that HTC and Direct Loan app has been submitted? Left message for Tim Smith.
| 2019-11-07 | Sent follow-up to Shannon's follow-up email asking for a timeline so that we can plan accordingly on our end.
| 2019-11-08 | We'll get a 2020 bond reservation and supplement the 2019 App with 2020 Certifications. Will target a February 2020 Board meeting. Need to send over the reservation withdrawal and new app for volume cap at same time so there's not a big gap with no reservation for Direct Loan purposes. Will plan on a February Board meeting. Andrew will keep them under them 2019 NOFA. Notified Jo Taylor to put PPR on hold. Need documentation that they purchased the land and final zoning approval.
| 2020-01-07 | Will submit for new bond reservation week of January 13th to hopefully have it issued that week for DL purposes.
| 2020-01-28 | Sent email on items needed - no objection resolution, 2020 certifications, final zoning ordinance and experience certificate.
| 2020-01-31 | Applicant had conversation with Andrew and they will be changing a few things in the application. The HAP contract now will not cover all of the units but only about 70. Notified REA that app should be put on hold for now.
| 2020-02-14 | Met with Andrew and REA to discuss next steps on this deal with all the changes proposed by Dave. I'll send a laundry list of items that we need with a deadline by which he needs to get it to us. Once we have a chance to go through it, then we'll schedule a call with Dave to walk through any issues. Will also suggest a call with HUD to confirm they're okay with cutting off 41 units and to discuss the URA requirements.
| 2020-03-11 | Have had multiple conversations with the applicant regarding items to be submitted. Still nothing. Kick-off call has been postponed with no date in mind. Made decision to move to May meeting.
20444 |  | Plano Kathryn Senior Living | Plano | Collin | 3 | 2020-01-13 | 2020-05-21 | Active | NC | Elderly | 252 | 252 | 2020-01-13 | 2020-07-11 | 30000000 | Plano PFC | 1835157 |  |  | N | West of Kathryn Road south side of 121 | 75025 | Kent Conine | (972) 979-6996 | kent@conine.com | Earnest Burke | (972) 423-4928
comment
20604 | 19468 | The Walzem | San Antonio ETJ | Bexar | 9 | 2020-02-24 | 2020-05-21 | Active | NC | General | 200 | 200 | 2020-03-12 | 2020-09-08 | 20000000 | TDHCA | 1326147 |  |  | N | 7810 Walzem Road | 78244 | Jay Johnson | (913) 671-3300 | jjohnson@cohenesrey.com | Teresa Morales | (512) 475-3344
comment | 2020-02-13 | Talked with Jay. Suggested that a new 2020 HTC application be submitted ASAP after Feb inducement meeting. Said he wants to close by April 15 and I said that wasn't going to happen. Will send him our distribution list and he said Bank of America is having calls already and he would have us added to them. He indicated that Jim Plummer already got Elizabeth up to speed and that she's been working on the deal. Not sure that's true but followed up with Elizabeth on 2/15/2020.
20602 | 3438 | Vermillion Apartments | Houston | Harris | 6 | 2020-04-03 | 2020-07-23 | Active | Acq/Rehab | General | 260 | 260 | 2020-03-17 | 2020-09-13 | 29000000 | TDHCA | 1373409 |  |  | N | 3360 Alice St. | 77021 | Russell Condas | (303) 586-2346 | rcondas@dominiuminc.com | Teresa Morales | (512) 475-3344
comment | Previous HTC award in 2003.
20446 | 19432 | St. Johns Square | San Antonio | Bexar | 9 | 2019-10-18 | 2020-03-26 | Approved | NC | General | 252 | 54 | 2020-01-24 | 2020-07-22 | 50000000 | Las Varas PFC | 473449 | 449524 |  | N | SEC St. Mary's and E Nueva St | 78205 | Dennis McDaniel | (512) 422-9162 | dennis@austinfairchild.org | Timothy Alcott | (210) 477-6633
comment |  | Applicant submitted the application fee around July 25, 2019 but decided to hold off on submitting the application. May need to issue a refund if application is not submitted within the next month or so.
| 2019-08-23 | Sarah Andre emailed and said that because they didn't get a bond reservation they won't be submitting the application. We'll be processing a refund.
| 2019-11-06 | Sarah Andre indicated that they'll be submitting updates to the application - will be changing up the unit mix.
| 2019-12-03 | MF started the review of the application.
| 2019-12-20 | REA conversation with applicant indicated they would be getting a new 2020 bond reservation.
| 2020-04-21 | Applicant returned the bond reservation and will be looking to obtain a new one maybe in August. Suggested they don’t submit the documents associated with the current Determination Notice since we'll have to re-issue the Notice.
20448 | 18458/19431 | Scharbauer Flats | Midland | Midland | 12 | 2019-06-24 | 2020-02-20 | Approved | NC | General | 300 | 300 | 2020-01-22 | 2020-07-20 | 40000000 | TSAHC | 2895615 | 2895615 | 0 | N | 2300 N Fairgrounds Road | 79705 | Jeff Spicer | (763)392-9875 | jeff.spicer@dominiuminc.com | Dave Danenfelzer | (512) 477-3562
comment | 2020-01-24 | Originally approved 9/5/2019. Changes in costs necessitated a re-evaluation of underwriting and new issuance of the Determination Notice.
20447 | 19472 | Franklin Park | Austin | Travis | 7 | 2019-09-27 | 2020-05-21 | Active | Acq/Rehab | General | 163 | 163 | 2020-01-14 | 2020-07-12 | 15000000 | Austin Affordable PFC Inc. | 749966 |  |  | N | 4509 E St. Elmo Road | 78744 | Ron Kowal | (512) 767-7796 | ronk@hacanet.org | Ron Kowal | (512) 767-7796
comment | 2019-12-20 | REA waiting on updated PCA. Not likley to happen until after the holidays. Applicant realizes it may mean a February Board meeting. Will need a new reservation anyway since not able to close under current one. Sent email to applicant asking about timing for a resolution since 2020 rule requires one for poverty rate issue. Might be able to stick with recommendation based on 2019 rules - need to run past legal.
| 2020-01-24 | Poverty rate not an issue. Since it's a 2020 application now, the poverty rate for 2020 is below the threshold. Will need 2020 certifications.
| 2020-04-02 | Received 2020 certifications; however, the NRA on the architect cert didn't match the existing rent schedule. Requested clarification from applicant.
20449 | 19469 | EMLI at Pecan Creek | Aubrey | Denton | 3 | 2019-08-23 | 2020-04-23 | Approved | NC | General | 254 | 254 | 2020-02-07 | 2020-08-05 | 20000000 | Denton County HFC | 1484333 | 1484333 | 0 | N | NWQ of Ike Byrom Rd and FM 1931 | 76227 | Richard Ashton | (940) 427-1160 | rashton@liberty42.com | Cheryl Knight | (940) 349-2830
comment | 2019-10-04 | Email from applicant indicated they are completing additional HUD required third party reports that are taking additional time. They indicated they would be withdrawing the reservation and won't be ready to go to the Board until January/February.
| 2019-10-12 | Notified Jo not to review the PPR since it'll be a while before they go to the Board
| 2019-10-20 | Sent email to applicant suggesting the application should be withdrawn since we don’t have a definitive timeline for moving forward. They plan to withdraw the current reservation and indicated they may be ready for a Jan/Feb Board meeting. It might be that they need to re-submit using a 2020 application and incorporating all deficiencies. 10/21/2019 - Applicant withdrew application. Will keep us posted on moving forward.
| 2019-11-15 | Applicant indicated they are ready to move forward with HUD. Confirmed that they'll be submitting the outstanding deficiencies from Shannon's review. Will need to then have a second review, and possibly plan for a January meeting. Once the new reservation is received, we'll need the 2020 certifications to supplement the application.
| 2019-12-20 | Need to check status of HUD application submission and confirm timing of new reservation with applicant.
| 2019-12-27 | Diamond indicated they aren't submitting the HUD app until January 20th. Made decision to move deal to February meeting and let REA know.
| 2020-01-24 | Still need county resolution and architect certification. Application submitted to HUD; we have a copy. New reservation needs to be issued before Board meeting.
| 2020-02-07 | Site will be annexed. Plan to get confirmation of annexation on March 5th and will follow-up with evidence. If received then no resolution from county will be required. Pushed to March.
| 2020-02-27 | Followed up with Richard on timing of resolution (still planned for March 5th?) and the 2020 architect cert with correct NRA.
| 2020-03-18 | Denton county delayed action on the resolution because of the elections. Told Richard that we'd be moving the application to the April meeting.
| 2020-04-02 | Resolution has been received. On track for April meeting; notified REA.
20451 | 19440 | Ventura at Parmer Lane | Austin ETJ | Travis | 7 | 2019-07-25 | 2019-10-10 | Closed | NC | General | 216 | 216 | 2020-02-05 | 2020-08-03 | 34000000 | Austin Affordable PFC, Inc. | 2189841 | 2189841 |  | N | 8407 E Parmer Lane | 78653 | Jeff Spicer | (763) 392-9875 | jeff.spicer@dominiuminc.com | Ron Kowal | (512) 477-4488
comment | 2020-01-30 | Applicant indicated they won't be able to close by the reservation deadline and will be getting a new reservation in 2020.
| 2020-02-07 | Received Cert of New Docket Number
| 2020-02-12 | Re-issued the Determination Notice
20452 |  | Enclave at Lake Pointe | Houston ETJ | Harris | 6 | 2020-02-12 | 2020-06-25 | Active | NC | Elderly | 132 | 132 | 2020-02-12 | 2020-08-10 | 14200000 | Harris County HFC | 723460 |  |  | N | 12400 N. Lake Houston Pkwy. | 77044 | Amay Inamdar | (713) 540-0122 | amay.inamdar@magellandev.com | Rene Martinez | (832) 248 - 4824
comment
20460 | 18423; 19400 | Villas del San Xavier | San Marcos | Hays | 7 | 7/27/2018; 9/27/2019 | 2019-12-12 | Approved | NC | Elderly | 156 | 156 | 2020-03-03 | 2020-08-30 | 25000000 | New Hope Cultural Education Facilities Finance Corp | 1059750 | 1059750 | 0 | N | 2301 South IH 35 | 78666 | Gina Marie Larson | (214) 212-6472 | ginamarie@gmlsenior affordablehousing.com | Maria Huynh | (972) 424-8501
comment | 2018-10-08 | Application was suspended from review pending updated application exhibits based on site control resolution.
| 2018-11-23 | Application was terminated due to lack of response and resolution to site control issues.
| 2018-11-26 | Talked with Tim Smith. They will not appeal the termination. Site control issues have been resolved. Tim will be re-submitting the application under the current 2018 reservation. We'll assign a 2019 number since it'll be getting a 2019 reservation in January. Will ask for 2019 certifications in January. Depending on when it's re-submitted we can tentatively target a February Board meeting.
| 2019-03-08 | A new individual was added to the developer org chart after the previous person (Michael Cordon) did not qualify for the experience. An experience letter was issued and the updated app docs were emailed to Jo Taylor for PPR.
| 2019-03-11 | Was determined through a PPR review that Spectrum is associated with a foreclosure. Makes the application ineligible under QAP and a Category 3 under the new PPR rules. Drafted a letter to the applicant for them to explain how they believe they are eligible. Will review response before determining whether termination is necessary.
| 2019-04-12 | Still waiting on response to foreclosure/ineligibility issue.
| 2019-04-15 | Phone call with Tim Smith. Indicated applicant is talking with San Marcos Housing Authority to come into the deal. Nothing in writing to that effect but informed Jo. Told Tim that he'll need to submit PPR documents at least 10 weeks before whenever they want to go to the Board. Will also probably need to refresh numbers. Might make sense to suspend application (wait until April 22 to see if there's an update from Tim) or consider it withdrawn if we have no idea on timeframe.
| 2019-05-28 | Emailed suspension letter to applicant for failure to resolve organizational structure issue/respond to staff enquiry letter from March 15th.
| 2019-08-06 | Applicant was able to find another CHDO to replace the prior. Will re-submit the org documents and updated term sheets and financing exhibits (in Excel and PDF) along with a narrative of what numbers changed.
| 2019-08-26 | Talked with Tim Smith who indicated they are in the process of updating the inducement to reflect an LP for the partnership instead of an LLC. Apparently the LLC structure is necessary to achieve the property tax exemption.
| 2019-09-27 | Applicant submitted the updates to the application. Requested November meeting, but will be targeting December based on submission date. Will treat similar to Primrose and do a review of the updated sections only on a new review sheet.
| 2019-11-11 | Applicant bought land. Exemption from taxes may only be from everything but city taxes - REA to confirm. Tim will send the settlement statement (it will show a price for more land than needed for this deal) and new legal description for all tracts.
| 2019-12-20 | Email from Shackelford indicated the deal did not close. Bond purchaser walked away from the deal.
| 2020-02-14 | Phone call with John Shackelford. He indicated they will not be closing under the 2019 bond reservation. Since they just got a new bond purchaser (BB&T) on board they are looking at an April closing. They didn't even have a draft BPA yet and purchaser just recently did a site visit. Suggested that once the new bond reservation comes out, he should contact staff to send him the cert of new docket number. Once we receive it we'll give it a new 2020 number and issue a 2020 Determination Notice.
| 2020-03-03 | New reservation was issued. Emailed No Changes cert so the Notice can be re-issued.
20450 |  | Mira Vista Apartments | San Antonio | Bexar | 9 | 2020-02-21 | 2020-05-21 | Active | NC | General | 312 | 312 | 2020-01-03 | 2022-12-31 | 28000000 | Las Varas PFC | 1783385 |  |  | N | 1226 Mira Vista | 78228 | Michael Hogan | (210) 682-1500 | mhogan@hoganre.com | David Nisivoccia | (210) 477-6262
comment
20453 | 18456; 19470 | Jackie Robinson Apartments | El Paso | El Paso | 11 | 2019-10-02 | 2019-12-12 | Approved | Acq/Rehab | General | 186 | 186 | 2020-02-11 | 2020-08-09 | 30000000 | Alamito Public Facilities Corp. | 1030373 | 1290195 | 0 | N | 421 Mangrum Circle | 79912 | Satish Bhaskar | (915) 849-3730 | sbhaskar@hacep.org | Art Provenghi | (915) 849-3709
comment | 2019-04-23 | Email from Janna on 3/13/19 indicated this deal was not going to close by the April 2019 BRB Reservation deadline. Can meet the 50% test with only $20M so will be requesting a new reservation. Janna indicated there have been no changes so upon issuance of the new reservation we'll need to send the Cert of No Changes. Once received we'll re-issue a 2019 Determination Notice. PPR could be a problem given issue with DeWetter and Kathy White.
| 2019-09-06 | Email from Janna indicated there have been delays with HUD but the deal is back on track. The cert of no changes was submitted to coincide with the new bond reservation. Requested additional information regarding numbers that may have changed considering it's been a while since the deal was approved. Requested an updated PPR.
| 2019-10-04 | Given the amount of time that has passed since the original docket number was withdrawn the Cert of No Changes won't work. Janna submitted revised numbers that was forwarded to REA on 10/5/2019. Requested an updated PPR but Jo said getting it done in time for November meeting might be tough. Suggested November meeting to REA for their analysis.
| 2019-10-17 | Compliance sent notice of Category 3 to applicant. Assume that PPR will go to Board in November but not sure if award will go too, considering prior Board approval despite Category 3. Need to talk with Beau but first see if that's what the applicant is expecting to happen.
| 2019-11-07 | PPR approved at November meeting - award will follow in December. Use same language for this BAR as was in Estates at Shiloh.
| 2020-01-09 | Emailed Janna about whether the deal closed, she indicated they are still going through the demo-dispo process with HUD and that they'll be cutting it close to make the current bond expiration date.
20419 | 2444 | Woodway Village | Austin | Travis | 7 | 2020-02-26 | 2020-06-25 | Active | Acq/Rehab | General | 160 | 160 | 2020-02-20 | 2020-08-18 | 30000000 | Austin Affordable PFC, Inc. | 1196513 |  |  | N | 4500 Nuckols Crossing Road | 78744 | Ron Kowal | (512) 767-7796 | ronk@hacanet.org | Ron Kowal | (512) 767-7796
comment
20454 |  | South Terrace Apartments | Waco | McLennan | 11 | 2020-03-05 | 2020-06-25 | Withdrawn | Acq/Rehab | General | 250 | 250 | 2020-01-31 | 2020-07-29 | 25000000 | Waco Public Facilities Corporation | 1452219 |  |  | N | 100 Kennedy Circle | 76706 | Milet Hopping | (254) 752-0324 | mileth@wacopha.org | Milet Hopping | (254) 752-0324
comment | 2020-03-19 | BRB website shows the reservation was withdrawn. They are in-line to receive another through the PFC.
| 2020-04-02 | All deficiencies from first review were cleared but since there's no reservation it's not being prioritized for a second review.
| 2020-04-26 | Application is in-line for a bond reservation.
20455 |  | Redwood | San Marcos | Hays | 7 | 2020-03-05 | 2020-06-25 | Active | NC | General | 296 | 296 | 2020-03-03 | 2020-08-30 | 50000000 | Capital Area Housing Finance Corporation | 2107712 |  |  | N | 15.51 acres on Redwood Road | 78666 | Jason L. Trevino | (512) 578-8488 | jtrevino@LDGdevelopment.com | James E. Shaw | (512) 347-9953
comment
20457 |  | Pinewood Apartments | Houston | Harris | 6 | 2020-03-06 | 2020-06-25 | Active | Acq/Rehab | General | 240 | 240 | 2020-03-03 | 2020-08-30 | 30000000 | Harris County Housing Finance Corporation | 1174359 |  |  | N | 5900 Greens Road | 77396 | Ryan Lunderby | (763) 354-5634 | rlunderby@dominiuminc.com | Elizabeth Bowes | (214) 365-0515
comment
20458 |  | Kinwood Apartments | McKinney | Collin | 3 | 2020-03-06 | 2020-06-25 | Active | Acq/Rehab | General | 200 | 200 | 2020-02-07 | 2020-08-05 | 30000000 | McKinney Housing Finance Corporation | 1245289 |  |  | N | 3300 North McDonald Street | 75071 | Ryan Lunderby | (763) 354-5634 | rlunderby@dominiuminc.com | Cristel Todd | (612) 376-4042
comment
20459 |  | Spring Villas | Austin | Travis | 7 | 2020-03-05 | 2020-06-25 | Active | NC | General | 304 | 302 | 2020-03-03 | 2020-08-30 | 45000000 | Travis County Housing Finance Corporation | 2295642 |  |  | N | 7430 Bluff Springs Road | 78744 | David Yarden | (818) 706-0694 | Dyarden@amcalhousing.com | Andrea Shields | (512) 854-9116
comment
20461 |  | Cascade at Onion Creek | Austin | Travis | 7 | 2020-03-11 | 2020-06-25 | Active | NC | General | 264 | 264 | 2020-03-03 | 2020-08-30 | 35000000 | Travis County Housing Finance Corporation | 1427509 |  |  | N | 11601 IH 35 SVRD NB | 78747 | Joel Pollack | (210) 643-1700 | jpollack@streamlineap.com | Andrea Shields | (512) 854-9116
comment
20465 | 19428; DID NOT CLOSE UNDER 2019 RESERVATION | Riverstone | San Marcos | Hays | 7 | 2019-07-19 | 2019-11-07 | Approved | NC | General | 336 | 336 | 2020-02-27 | 2020-08-25 | 50000000 | Capital Area HFC | 2349942 | 2349942 | 0 | N | 1430 Wonder World Drive | 78666 | Chase Darst | (502) 916-2413 | cdarst@ldgdevelopment.com | James E. Shaw | (512) 347-9903
comment | 2019-06-30 | Applicant submitted the application too early since their bond reservation will need to come out of the collapse on August 15. Staff will consider the application withdrawn for purposes of starting the 30-day clock on the reservation. We will keep the fee for convenience but will require they re-submit the application within the 30-day window.
| 2019-07-19 | Applicant re-submitted the Application.
| 2019-10-02 | Applicant still in the process of figuring out what the total site acreage will be. Decided to delay to the November meeting in hopes they'll know more in order to avoid a potential amendment later on if the density changes by more than 5%.
| 2019-11-07 | Applicant indicated the permitting process is taking longer than anticipated. They expect permits the week the reservation expires. Will be seeking a 2020 bond reservation as a plan B. I indicated that if that happens they'll need to submit the Certification (within 4 months of when the prior reservation is withdrawn) and we'll need to update PPR before issuing a 2020 Determination Notice.
| 2020-01-14 | Per Jim Shaw, the project ran into permit issues. Will get a 2020 bond reservation and close shortly thereafter. Will need the signed certification, assign a 2020 app ID and re-issue the Determination Notice.
| 2020-02-27 | New reservation issued. Waiting for applicant to contact us regarding new Determination Notice, etc.
19438 | WILL NOT CLOSE UNDER 2019 | Legacy Seniors | Round Rock | Williamson | 7 | 2019-08-23 | 2019-11-07 | Approved | NC | Elderly | 157 | 157 | 2020-03-03 | 2020-08-30 | 20000000 | Capital Area HFC | 732029 | 732029 |  | N | 1001 University Boulevard | 78665 | Bobbi Jo Lucas | (402) 341-0888 | blucas@cstonellc.net | Jim Shaw | (512) 347-9903
comment | 2019-12-03 | Received a call from Robbye who indicated they'll be returning the 2019 reservation and getting a new one in 2020. Once the new reservation is issued we will send them the Certification of No Changes and upon receipt we'll administratively re-issue the Determination Notice.
| 2020-03-23 | Phone call with Robbye indicated the structure is changing from public offering to private placement. Suggested she provide a summary of what implication that has on the deal overall in order for us to determine whether it's material such that it would need to go back to the Board or if not material then we could just administratively re-issue the Determination Notice.
20463 |  | Trinity Oaks | Sulpher Springs | Hopkins | 4 | 2020-04-06 | 2020-07-23 | Active | Acq/Rehab | Elderly | 48 | 48 | 2020-03-24 | 2020-09-20 | 2129000 | TSAHC | 497000 |  |  | Y | 600 Woodlawn | 75482 | Dan Allgeier | (214) 277-4839 | dan@lakewoodmanagement.com | Dave Danenfelzer | (512) 477-3562
comment
20464 |  | Pine Terrace | Mt. Pleasant | Titus | 4 | 2020-04-06 | 2020-07-23 | Active | Acq/Rehab | Elderly | 76 | 76 | 2020-03-24 | 2020-09-20 | 3371000 | TSAHC | 210127 |  |  | Y | 1612 Amy Drive | 75455 | Dan Allgeier | (214) 277-4839 | dan@lakewoodmanagement.com | Dave Danenfelzer | (512) 477-3562
comment
20609 |  | Pecan Grove | Seguin | Guadalupe | 9 | 2020-04-03 | 2020-07-23 | Active | NC | General | 198 | 198 | 2020-04-03 | 2020-09-30 | 26000000 | TDHCA | 1353160 |  |  | N | 1231 West Court Street | 78155 | Jason Trevino | (512) 578-8488 | jtrevino@ldgdevelopment.com | Teresa Morales | (512) 475-3344
comment | 2019-07-24 | Requested update on whether they'll be ready to submit volume cap application on August 15th.
| 2019-08-08 | Applicant indicated they won't get permits until end of January and said a February Board meeting would make sense. Will take down volume cap in January 2020. They indicated they would submit the HTC application in December.
| 2019-11-07 | Applicant indicated they are trying to get the Seguin Housing Authority on board (to possibly partner with). The pre-app doesn't reflect them in the deal. They indicated they are still shopping the deal but may end up with Redstone/R4 as reflected in the pre-app. Will touch base with them in December confirming we'll be submitting for the reservation in January and they'll be ready to submit the full application.
| 2020-04-08 | Received no objection resolution in 2019. Has a poverty issue that will need a resolution. Suggested to Jason that he try to obtain but if he can't then submit a waiver request stating reasons why and how related to COVID-19.
20466 | 04402 | Blue Water Gardens | Hereford | Deaf Smith | 1 | 2020-04-03 | 2020-07-23 | Active | Acq/Rehab | General | 132 | 132 | 2020-02-27 | 2020-08-25 | 16750000 | Panhandle Regional HFC | 730914 |  |  | N | 612 N. Irving Street | 79045 | Ina K. Spokas | (463) 204-8812 | ina.spokas@kcgcompanies.com | Michael Carr | (806) 360-2060
comment
20467 |  | Greenline North | San Antonio | Bexar | 9 | 2020-04-03 | 2020-07-23 | Active | NC | General | 292 | 292 | 2020-03-03 | 2020-08-30 | 50000000 | San Antonio Housing Trust Finance Corporation | 1946883 |  |  | N | 7402 S. New Braunfels Avenue | 78223 | Lucila Dias | (210) 408-3152 | lucila@franklindev.net | Pedro Alanis | (210) 735-2772
comment
20456 |  | The Hollows | Channelview CDP | Harris | 6 | 2020-04-06 | 2020-07-23 | Active | NC | General | 192 | 192 | 2020-02-20 | 2020-08-18 | 20000000 | Harris County Housing Authority | 1043287 |  |  | N | Southeast corner of Wallisville Road and Dell Dale Street | 77530 | Jason Trevino | (512) 578-8488 | jtrevino@ldgdevelopment.com | Samson Babalola | (713) 669-4572
comment
20468 |  | Preserve at the Port | San Antonio | Bexar | 9 | 2020-04-06 | 2020-07-23 | Active | Acq/Rehab | General | 384 | 384 | 2020-03-03 | 2020-08-30 | 37000000 | San Antonio Housing Trust Vinance Corporation | 1654968 |  |  | N | 402 Gillmore Avenue | 78226 | Holly Thoman | (210) 569-9354 | hollyhthoman@gmail.com | Nicole Collazo | (210) 735-2772
comment
20471 |  | Northwood Apartments | Houston ETJ | Harris | 6 | 2020-04-07 | 2020-07-23 | Active | NC | General | 288 | 288 | 2020-03-19 | 2020-09-15 | 30000000 | Harris County Housing Authority | 2378498 |  |  | N | Southeast corner of Eastex Freeway and Hamill Road | 77039 | Jason Trevino | (512) 578-8488 | jtrevino@ldgdevelopment.com | Samson Babalola | (713) 669-4572
comment
20607 |  | Avenue on 34th Apartments | Houston | Harris | 6 | 2020-03-19 | 2020-04-23 | Withdrawn | NC | General | 70 | 56 | N/A | N/A | 8000000 | TDHCA | 324609 |  |  | N | 2136 W. 34th St. | 77018 | Jason Holoubek | (713) 864-8099 | jasonh@avenuecdc.org | Jeff Smith | (713) 461-2749
comment | 2020-04-20 | Decided to stick with local issuer reservation
20613 |  | Riverside Senior | Fort Worth | Tarrant | 3 | TBD | 2020-06-25 | Pre-Application | NC | Elderly | 264 | 264 | TBD | TBD | 36000000 | TDHCA | 1818482 |  |  | N | 8101 North Riverside Drive | 76137 | Melissa Fisher | (972) 701-5558 | mfisher@rise-residential.com | Teresa Morales | (512) 475-3344
comment
20610 |  | Terrace at Southern Oaks | Dallas | Dallas | 3 | TBD | 2020-06-25 | Pre-Application | NC | General | 300 | 300 | TBD | TBD | 50000000 | TDHCA | 2000114 |  |  | N | 22 acres Southern Oaks Blvd. | 75216 | Jason Trevino | (512) 578-8488 | jtrevino@ldgdevelopment.com | Teresa Morales | (512) 475-3344